## Slide 1: Technical Workshops
IEEE National Capital Area
v01

## Slide 2: Defining “Technical Workshop”
A Technical Workshop is an educational event
  Provides deep learning on an engineering topic of interest
  More detailed than chapter talks
  Registration is required and capacity is limited
  Most have been ½ to 1 day long
  Usually there is a cost to attend
  Typically held over a weekend and may include lunch
They require many, many hours of preparation
  So why do them?

## Slide 3: Why Hold Workshops
Accessible and interesting
  There’s time to get all attendees on the same page
  There’s time to explore and demonstrate
They can be profitable
  With careful planning they can replace some declining revenue
  Members like them!
    Can provide CEU/PDH credits
    Feedback from recent Northern VA events was positive and the created a long wait list

## Slide 4: About These Slides
These slides outline things to consider when planning a workshop
  Based on lessons from Northern VA Section’s “Build an Internet of Things Weather Station” taught by Karl Berger in June 2016
Goal is to assure success, NOT to scare away prospective ideas
  Variations possible

## Slide 5: The Proposal
Technical Workshops should be approved by AdCom
  Generates wider input, support, and attendee base
  Event results reflect on the section
  Advance section funding requires motion
    “Motion to hold advance nuclear plasma workshop at a cost of $1,000,000 to be recovered by registration fees”
Proposal must contain sufficient information to decide
  Topic and instructor(s)
    May be chosen in any order or together
  Target date and venue
  Financial plan and cost estimate (if any)

## Slide 6: Good Topics
Relevant to a Society/Council and “fresh”...
  i.e. “Raspberry Pi” in 2014, “Internet of Things” in 2016
...or classical, fundamental, and always useful
  Circuit theory, programming in C, etc.
Combine Theory and Practice
  Bridges academic conferences and Maker-style events
  More accessible to wide-ranging backgrounds
  Activity-oriented: assemble, measure, type...
    Northern VA’s workshop are specifically billed as part of a “Hands-On” series, though some chapters may be more amenable than others

## Slide 7: Good Instructors
Strong knowledgeable about the specific topic
  Industry experience is particularly useful
  Narrow and deep is usually better than wide and shallow
Some teaching experience
  Able to keep the class moving and avoid rat holes
  Enthusiasm keeps students engaged
Two instructors divide preparation and class workload
  Also provides redundancy
Can spare a lot of time
  They will drive the curriculum

## Slide 8: Target Timeframe and Venue
Pick a Saturday
  Enough time to prepare, order materials, and practice
  Avoid conflict with other IEEE/similar events
    Nov/Dec, Jan, and summer may also be harder to get interest
Choose a location with sufficient capacity
  Verify computers, WiFi, Internet access if needed
  Accessibility to Washington/Northern VA increases turnout
  Free venues keep registration costs low
    Ask section officers about no-cost options
Subject to change until advertising begins

## Slide 9: Financial Plan
Registration fees and estimated attendance
  Optional discounts to students, seniors, military
Materials, food, venue, and gift expenses
  Including a “take home” may increase interest
    For IoT course, students kept finished weather station
    Could be other assembled device, book, CD/DVD, etc.
Up front expenditures and expected net
  To count for L31 chapter should be willing to contribute to up front expenses
    Active chapters can always request more funds
  Aim for break-even or reasonable profit

## Slide 10: Obtain Approval
Circulate the proposal in advance
  Create a one-page course flyer
    See past examples for what to cover
  Put together financials
  Lets people study and ask questions beforehand
Come to the meeting
  The instructor(s) should present
    Especially for first time people and courses
  Be prepared to answer questions and accept revisions
If rejected rinse, lather, repeat...

## Slide 11: Prepare Original Content
Create course slides, handouts, and other media
  Organize into modular, 15-45 minute lessons
  Provide detailed steps for lab activities
  Connect to IEEE activities when possible
  Reuse internal content, but limit use of non-IEEE docs
Put together course syllabus/outline
  Include intros, logistics, lunch break
Expect to spend more time on this than anything else

## Slide 12: Differentiate Content
People can find recipes to build almost anything
  YouTube, Maker Faires, MOOCs, Web Sites, etc
An IEEE Workshop should provide more
  Deeper understanding of how things work
  Comparison of design approaches and component choices
  Appreciation of the engineering process
  Description of related fields and ideas
  Historical context, where appropriate

## Slide 13: Reserve The Location
Choose a date from available options
  Verify instructor availability
  No conflicts with other events
  No scheduled maintenance on necessary resources
Check special weekend requirements
  Building access instructions
  Parking options and costs
Make payment arrangements, if needed

## Slide 14: Order Materials and Food
If needed order kit parts in far advance
  Create lab instructions using actual materials
  IoT workshop parts came from China
  Several had to be returned/exchanged
Order lunch and optional morning coffee
  Check with people familiar with the location
    They may have relationships with local COSI, Potbelly, etc
  Include some vegetarian options
  Have volunteers pick up or pay for delivery

## Slide 15: Apply For CEU/PDH Credits
Request approval online
  https://www.ieee.org/education_careers/education/ceus/application.html
They will explain what must be done after course to receive credits
  Note: the CEU/PDH evaluation form is not very good for feedback about the course – make up a separate course feedback form for students who do not need credits
  Typically 1 PDH per hour of class
Should take only a few days
  Follow up if you don’t hear back
  Ask Debi Siering (siering@ieee.org) for help

## Slide 16: Create vTools Registration
One entry per workshop (not per section, chapter)
  A catchy, descriptive title and category
  Detailed event description and agenda
  Start and stop times and clear, detailed location
  Contact information and instructor(s) biography
  Student prequisities and minimum age
  Specify registration prices, discounts, maximum attendees
  Refund policy
Ask for review and check guidelines
    http://sites.ieee.org/nova/resources/communication/event-post-guidelines/

## Slide 17: Promote The Event
Finalize the one page proposal course flyer
  Update anything that changed
Have eNotice sent to section
  Neighboring sections also if appropriate
  Region secretary can send to other areas
  Target students!
Advertise on social media
  Twitter, Facebook,...
Revisit periodically until fully enrolled

## Slide 18: Manage Registrations
vTools has quirks...
  PayPal works better than credit cards
  Unconfirmed payments count againt maximum
    Individuals can create them unknowingly
Clean out unconfirmed entries periodically
  Checking with registrant if they think they payed
Maintain a wait list of people after it fills
Refund users with legitimate reasons to cancel
  Expect exceptions! Typically have to mail a check

## Slide 19: Manage Hardware, Internet Risks
Paying increases expectations
  Have contingency plans
If the course involves equipment
  Order spare parts and bring extra cables, power cords,...
If participants must download software
  Freeze the version a few days before the class
  Set up a local server
    Use LAMP on spare laptop or media server built-in to routers
  Verify necessary files are free of malware
    Submit to VirusTotal: https://www.virustotal.com/

## Slide 20: Manage Software Risks
If attendees bring their own laptops
  Test on multiple operating systems
  Remind them to update OS and AV before class
There may be other subtle compatiblity issues
  Provide download instructions in advance
    But still accommodate in-class download
  Develop a script members can download in advance to ensure their system will work
    Verify the right OS or .Net version, admin privileges, sufficient disk space, memory, etc

## Slide 21: As The Course Day Approaches
Do a practice run on location
  Shake out course and get helpers up to speed
Send email to registrants
  Remind where, when, what they have to bring
  Include agenda and number to call if weather is bad
Verify food order
  Double check quantity and special dietary needs
  Ask local shops to sponsor/discount coffee and pastries
Print sign-in sheet and course evaluation forms
Purchase thank-you gifts

## Slide 22: Day Of The Course
Arrive early so you can start on time
  Make sure room is set up
  Put out/circulate sign-in sheet and remind people to use it
Greet arrivals and introduce the instructors
Keep the course moving
  You are the MC! Pull people out of rat holes
  Record unanswered questions
Have fun!
  If you’re not, the participants won’t either

## Slide 23: Immediately After
Thank everyone who contributed
  Especially the speaker
  Present the instructor(s) with a small gift or take to dinner
Collect sign-in sheet
Distribute and collect evaluation forms
  People wanting CEU/PDH credits must complete a special form
If appropriate encourage people to take their project
Ensure the room is in good condition
  Discard trash, return furniture, turn out lights, etc

## Slide 24: Within A Few Days After
Follow up on any questions
  Send info about IEEE to people who asked
Complete the paperwork
  Submit L31 – Create from vTools entry
  Submit CEU/PDH requests
  Summarize course feedback
Post final slides and materials online
Thank those who helped
Analyze the financials

## Slide 25: Final Thought
The “Build an Internet of Things Weather Station” workshop ran a deficit...
  Cost about $350 more than it made mostly due to component returns
...but on every other measure it was a success
  Full registration
  Uniformly positive feedback
  Attendees participating in other activities
  Long wait list
Try something!

## Slide 26: Additional Help
People want to help hold workshops
  It’s rewarding and looks good on a resume
Ask for help
  Start with your section officers and AdCom
nova.chair@ieee.org tony.ivanov@ieee.org

## Slide 27: Questions?